## L2 Template for upload
Milestone | Task | Unit | Qty | Progress | Start | End | Dept
220/33kV, 80MVA Power Transformer | RFQ to Vendors | Nos | 1 | WIP | 2022-05-25 | 2022-05-26 | Procurement
220/33kV, 80MVA Power Transformer | Ordering | Nos | 1 | WIP | 2022-05-27 | 2022-06-17 | Procurement
GEPDEC Milestone | Site Survey |  |  | Completed | 2021-09-24 | 2021-09-24 | Civil
GEPDEC Milestone | Conducting of Soil Investinagtion and earth resisitivity |  |  | WIP | 2021-10-24 | 2021-10-24 | Civil
Formulas:
End = [Start]

## List
Nos | Yet to Start | Civil
Kgs | WIP | Mechanical
Ltrs | Hold | Sales
Packet | Completed | Information Technology
| Abandoned | Procurement
Spare Parts