## Project - Schedule - External
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Power Augmentation of New Oxygen Plant at Durgapur Steel Plant
Enter Company Name in cell B2. | Gepdec Infratech Limited
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. | Project Start: | [36 empty] | 2023-07-20
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Display Month: |  |  |  |  | 1 | 8 |  | 2022-02-01 |  |  |  | 2022-03-01 |  |  | 2022-03-31 | 2022-04-01 |  |  |  | 2022-05-01 |  | 2022-05-23 |  | 2022-06-01 |  |  |  | 2022-07-01 | 2022-07-15 |  |  | 2022-08-01 |  |  |  | 2022-09-01 |  |  |  | 2022-10-01 |  |  | 2022-10-31 | 2022-11-01 |  |  |  | 2022-12-01 |  | 2022-12-23 |  | 2023-01-01 |  |  |  | 2023-02-01 | 2023-02-15 |  |  | 2023-03-01 |  |  |  | 2023-04-01 |  |  |  | 2023-05-01 |  | 2023-05-23 |  | 2023-06-01 |  |  |  | 2023-07-01 | 2023-07-15 |  |  | 2023-08-01 |  |  |  | 2023-09-01 | 2023-09-15 |  |  | 2023-10-01
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 1900-01-06 to 2023-10-31
| TASK |  | Unit | Qty | PROGRESS | START | END | Days | time axis 1900-01-06 to 2023-10-31
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | DSP MILESTONE / LOA
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Date of LOA (SAIL DSP) |  |  |  |  | 2022-02-23 | 2022-02-23 | 1
| Agreement date/Vendor Registeration at DSP |  |  |  |  | 2022-03-22 | 2022-03-22 | 1
| Project Timeline |  |  |  |  | 2022-03-22 | 2023-09-13 | 540
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | GEPDEC MILESTONE
| Site Survey |  |  |  |  | 2021-09-24 | 2021-09-24 | 1
| Conducting of Soil Investinagtion and earth resisitivity |  |  |  |  | Completed
| Finalisation of contractor for Site |  |  |  |  | 2022-04-10 | 2022-04-30 | 21
| Mobilisation of Workpower - Civil Manpower |  |  |  |  | 2022-05-05 | 2022-05-15 | 11
| Completion of Design & Engineering |  |  |  |  | 2022-03-15 | 2022-10-30 | 230
| Completion of Delivery of Supply Items |  |  |  |  | 2022-04-30 | 2023-04-08 | 344
| Completion of Civil activities. |  |  |  |  | 2022-05-15 | 2023-07-03 | 415
| Completon of Erection Activities |  |  |  |  | 2022-11-10 | 2023-05-30 | 202
| Testing & Commissioning |  |  |  |  | 2023-03-01 | 2023-08-15 | 168
| ENGINEERING |  |  |  |  | 2022-03-15 | 2022-10-30 | 230
Electrica | Basic Engineering (Electrical and Civil) |  |  |  |  | 2022-03-15 | 2022-05-13 | 60
| Detail Engineering (Electrical) |  |  |  |  | 2022-05-16 | 2022-07-29 | 75
| Detail Engineering (Civil) |  |  |  |  | 2022-05-16 | 2022-10-19 | 157
| Equipment Engineering |  |  |  |  | 2022-04-04 | 2022-10-16 | 196
| Approval from CET |  |  |  |  | 2022-03-29 | 2022-10-30 | 216
Sample phase title block | PROCUREMENT - ORDER PLACEMENT, DRAWING SUBMISSION & APPROVAL, MANUFACTURING, DISPATCH, RECEIVE AT SITE |  |  |  |  | 2022-04-30 | 2023-04-08 | 344
| 220 kV Equipment |  |  |  |  | 2022-04-30 | 2023-02-21 | 298
| 220/33kV, 80MVA Power Transformer |  | Nos | 1
|  | RFQ to Vendors |  |  |  | 2022-04-30 | 2022-04-30 | 1
|  | Ordering |  |  |  | 2022-05-01 | 2022-05-22 | 21
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-05-23 | 2022-06-13 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-06-14 | 2022-06-28 | 14
|  | Release of MFC |  |  |  | 2022-06-28 | 2022-06-28 | 1
|  | Manufacturing Lead time |  |  |  | 2022-06-29 | 2022-11-26 | 150
|  | Inspection and Dispatch |  |  |  | 2022-11-27 | 2022-12-09 | 12
|  | Receipt at Site |  |  |  | 2022-12-10 | 2022-12-18 | 9
| 220KV Isolator (Including 24 nos. BPI) |  | Set | 4
|  | RFQ to Vendors |  |  |  | 2022-05-25 | 2022-05-26 | 1
|  | Ordering |  |  |  | 2022-05-27 | 2022-06-17 | 21
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-06-18 | 2022-07-09 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-07-10 | 2022-07-24 | 14
|  | Release of MFC |  |  |  | 2022-07-24 | 2022-07-24 | 1
|  | Manufacturing Lead time |  |  |  | 2022-07-25 | 2022-10-23 | 90
|  | Inspection and Dispatch |  |  |  | 2022-10-24 | 2022-11-08 | 15
|  | Receipt at Site |  |  |  | 2022-11-09 | 2022-11-17 | 9
| 220kV Circuit Breaker |  | Set | 1
|  | RFQ to Vendors |  |  |  | 2022-06-13 | 2022-06-14 | 1
|  | Ordering |  |  |  | 2022-06-15 | 2022-06-30 | 15 | [84 empty] | 299
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-07-01 | 2022-07-22 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-07-23 | 2022-08-13 | 21
|  | Release of MFC |  |  |  | 2022-08-13 | 2022-08-13 | 1
|  | Manufacturing Lead time |  |  |  | 2022-08-14 | 2022-10-28 | 75
|  | Inspection and Dispatch |  |  |  | 2022-10-29 | 2022-11-13 | 15
|  | Receipt at Site |  |  |  | 2022-11-14 | 2022-11-22 | 9
| 220kV Lighting Arrestor |  | Nos | 3
|  | RFQ to Vendors |  |  |  | 2022-07-18 | 2022-07-18 | 1
|  | Ordering |  |  |  | 2022-07-19 | 2022-08-03 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-08-04 | 2022-08-25 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-08-26 | 2022-09-16 | 21
|  | Release of MFC |  |  |  | 2022-09-16 | 2022-09-16 | 1
|  | Manufacturing Lead time |  |  |  | 2022-09-17 | 2022-12-01 | 75
|  | Inspection and Dispatch |  |  |  | 2022-12-02 | 2022-12-17 | 15
|  | Receipt at Site |  |  |  | 2022-12-18 | 2022-12-26 | 9
| 220kV Current Transformer |  | Nos | 3
|  | RFQ to Vendors |  |  |  | 2022-06-15 | 2022-06-15 | 1
|  | Ordering |  |  |  | 2022-06-16 | 2022-07-01 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-07-02 | 2022-07-23 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-07-24 | 2022-08-14 | 21
|  | Release of MFC |  |  |  | 2022-08-14 | 2022-08-14 | 1
|  | Manufacturing Lead time |  |  |  | 2022-08-15 | 2022-10-29 | 75
|  | Inspection and Dispatch |  |  |  | 2022-10-30 | 2022-11-14 | 15
|  | Receipt at Site |  |  |  | 2022-11-15 | 2022-11-23 | 9
| 220kV BPI for Bus |  | Nos | 18
|  | RFQ to Vendors |  |  |  | 2022-07-21 | 2022-07-21 | 1
|  | Ordering |  |  |  | 2022-07-22 | 2022-08-05 | 14
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-08-06 | 2022-08-20 | 14
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-08-21 | 2022-09-04 | 14
|  | Release of MFC |  |  |  | 2022-09-04 | 2022-09-04 | 1
|  | Manufacturing Lead time |  |  |  | 2022-09-05 | 2022-11-04 | 60
|  | Inspection and Dispatch |  |  |  | 2022-11-05 | 2022-11-20 | 15
|  | Receipt at Site |  |  |  | 2022-11-21 | 2022-11-29 | 9
| Bay Marshelling Boxes in 220kV yard |  | Nos | 1
|  | RFQ to Vendors |  |  |  | 2022-08-20 | 2022-08-20 | 1
|  | Ordering |  |  |  | 2022-08-21 | 2022-09-05 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-09-06 | 2022-09-27 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-09-28 | 2022-10-19 | 21
|  | Release of MFC |  |  |  | 2022-10-19 | 2022-10-19 | 1
|  | Manufacturing Lead time |  |  |  | 2022-10-20 | 2022-12-19 | 60
|  | Inspection and Dispatch |  |  |  | 2022-12-20 | 2023-01-04 | 15
|  | Receipt at Site |  |  |  | 2023-01-05 | 2023-01-13 | 9
| Disc Insulator in 220kV yard |  | Nos | 180
|  | RFQ to Vendors |  |  |  | 2022-08-20 | 2022-08-20 | 1
|  | Ordering |  |  |  | 2022-08-21 | 2022-09-05 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-09-06 | 2022-09-27 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-09-28 | 2022-10-19 | 21
|  | Release of MFC |  |  |  | 2022-10-19 | 2022-10-19 | 75
|  | Manufacturing Lead time |  |  |  | 2022-10-20 | 2022-12-19 | 60
|  | Inspection and Dispatch |  |  |  | 2022-12-20 | 2023-01-04 | 15
|  | Receipt at Site |  |  |  | 2023-01-05 | 2023-01-13 | 9
| CRP (MRS Control room Building) |  | Lot | 1
|  | RFQ to Vendors |  |  |  | 2022-07-01 | 2022-07-01 | 1
|  | Ordering |  |  |  | 2022-07-02 | 2022-07-16 | 14
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-07-17 | 2022-08-07 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-08-08 | 2022-08-29 | 21
|  | Release of MFC |  |  |  | 2022-08-29 | 2022-08-29 | 110
|  | Manufacturing Lead time |  |  |  | 2022-08-30 | 2022-10-29 | 60
|  | Inspection and Dispatch |  |  |  | 2022-10-30 | 2022-11-14 | 15
|  | Receipt at Site |  |  |  | 2022-11-15 | 2022-11-23 | 9
| SCADA |  | Lot | 1
|  | RFQ to Vendors |  |  |  | 2022-07-01 | 2022-07-01 | 1
|  | Ordering |  |  |  | 2022-07-02 | 2022-07-17 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-07-18 | 2022-08-08 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-08-09 | 2022-08-30 | 21
|  | Release of MFC |  |  |  | 2022-08-30 | 2022-08-30 | 1
|  | Manufacturing Lead time |  |  |  | 2022-08-31 | 2022-12-19 | 110
|  | Inspection and Dispatch |  |  |  | 2022-12-20 | 2023-01-04 | 15
|  | Receipt at Site |  |  |  | 2023-01-05 | 2023-01-13 | 9
| HT Cables (3C*400 sq.mm) |  | Mtr | 1500
|  | RFQ to Vendors |  |  |  | 2022-04-30 | 2022-04-30 | 1
|  | Ordering |  |  |  | 2022-05-01 | 2022-05-16 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-05-17 | 2022-06-07 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-06-08 | 2022-06-29 | 21
|  | Release of MFC |  |  |  | 2022-06-29 | 2022-06-29 | 1
|  | Manufacturing Lead time |  |  |  | 2022-06-30 | 2022-11-12 | 135
|  | Inspection and Dispatch |  |  |  | 2022-11-13 | 2022-11-28 | 15
|  | Receipt at Site |  |  |  | 2022-11-29 | 2022-12-07 | 9
| LT Power / Control Cables and accesssories |  | Mtr | 22900
|  | RFQ to Vendors |  |  |  | 2022-06-30 | 2022-06-30 | 1
|  | Ordering |  |  |  | 2022-07-01 | 2022-07-16 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-07-17 | 2022-08-07 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-08-08 | 2022-08-29 | 21
|  | Release of MFC |  |  |  | 2022-08-29 | 2022-08-29 | 1
|  | Manufacturing Lead time |  |  |  | 2022-08-30 | 2023-01-27 | 150
|  | Inspection and Dispatch |  |  |  | 2023-01-28 | 2023-02-12 | 15
|  | Receipt at Site |  |  |  | 2023-02-13 | 2023-02-21 | 9
| Cable Termination Kits - Straight Through & End Termaintion |  | Lot | 1
|  | RFQ to Vendors |  |  |  | 2022-07-15 | 2022-07-15 | 1
|  | Ordering |  |  |  | 2022-07-16 | 2022-07-31 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-08-01 | 2022-08-22 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-08-23 | 2022-09-13 | 21
|  | Release of MFC |  |  |  | 2022-09-13 | 2022-09-13 | 1
|  | Manufacturing Lead time |  |  |  | 2022-09-14 | 2022-12-13 | 90
|  | Inspection and Dispatch |  |  |  | 2022-12-14 | 2022-12-29 | 15
|  | Receipt at Site |  |  |  | 2022-12-30 | 2023-01-07 | 9
| Cable accessories |  | Lot | 1
|  | RFQ to Vendors |  |  |  | 2022-07-15 | 2022-07-15 | 1
|  | Ordering |  |  |  | 2022-07-16 | 2022-07-31 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-08-01 | 2022-08-22 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-08-23 | 2022-09-13 | 21
|  | Release of MFC |  |  |  | 2022-09-13 | 2022-09-13 | 1
|  | Manufacturing Lead time |  |  |  | 2022-09-14 | 2022-12-13 | 90
|  | Inspection and Dispatch |  |  |  | 2022-12-14 | 2022-12-29 | 15
|  | Receipt at Site |  |  |  | 2022-12-30 | 2023-01-07 | 9
| Cable Trench (including bridge, cable tray etc.) |  | Mtr | 904
|  | RFQ to Vendors |  |  |  | 2022-08-01 | 2022-08-01 | 1
|  | Ordering |  |  |  | 2022-08-02 | 2022-08-17 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-08-18 | 2022-09-08 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-09-09 | 2022-09-30 | 21
|  | Release of MFC |  |  |  | 2022-09-30 | 2022-09-30 | 1
|  | Manufacturing Lead time |  |  |  | 2022-10-01 | 2022-12-30 | 90
|  | Inspection and Dispatch |  |  |  | 2022-12-31 | 2023-01-15 | 15
|  | Receipt at Site |  |  |  | 2023-01-16 | 2023-01-24 | 9
| Erection Hardware (220kV, 33kV, 11kV) |  | Lot | 1
|  | RFQ to Vendors |  |  |  | 2022-06-18 | 2022-06-18 | 1
|  | Ordering |  |  |  | 2022-06-19 | 2022-07-04 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-07-05 | 2022-07-20 | 15
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-07-21 | 2022-08-05 | 15
|  | Release of MFC |  |  |  | 2022-08-05 | 2022-08-05 | 1
|  | Manufacturing Lead time |  |  |  | 2022-08-06 | 2022-10-05 | 60
|  | Inspection and Dispatch |  |  |  | 2022-10-06 | 2022-10-21 | 15
|  | Receipt at Site |  |  |  | 2022-10-22 | 2022-10-30 | 9
| Erection Hardware (electrical equipment, panels, cabling, jointing & termination kits for cables, lighting and earthing like cable trays, GI conduits, M.S. angles, channels, flats, clamps, hangers, supporting brackets, cable lugs, ferrules, glands, GI wire, chequered plates, nuts, bolts, washers and all related items) - both 33kV and 11kV |  | Lot | 1
|  | RFQ to Vendors |  |  |  | 2022-06-18 | 2022-06-18 | 1
|  | Ordering |  |  |  | 2022-06-19 | 2022-07-04 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-07-05 | 2022-07-20 | 15
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-07-21 | 2022-08-05 | 15
|  | Release of MFC |  |  |  | 2022-08-05 | 2022-08-05 | 1
|  | Manufacturing Lead time |  |  |  | 2022-08-06 | 2022-10-05 | 60
|  | Inspection and Dispatch |  |  |  | 2022-10-06 | 2022-10-21 | 15
|  | Receipt at Site |  |  |  | 2022-10-22 | 2022-10-30 | 9
| Structure Material including Foundation Bolt |  | MT | 80
|  | Placement of Offer |  |  |  | 2022-05-15 | 2022-05-15 | 1
|  | Submission of Drawing |  |  |  | 2022-05-16 | 2022-05-31 | 15
|  | Receipt of Drawing Approval |  |  |  | 2022-06-01 | 2022-06-16 | 15
|  | Manufacturing Claearance |  |  |  | 2022-06-17 | 2022-07-02 | 15
|  | Inspection & issuance of Inspection Certificate |  |  |  | 2022-07-02 | 2022-07-02 | 1
|  | Manufacturing Lead time |  |  |  | 2022-07-03 | 2022-09-16 | 75
|  | Inspection and Dispatch |  |  |  | 2022-09-17 | 2022-10-02 | 15
|  | Receipt at Site |  |  |  | 2022-10-03 | 2022-10-11 | 9
| Earthing Material (MS Rod and flat) |  | Mtr | 5800
|  | RFQ to Vendors |  |  |  | 2022-06-18 | 2022-06-18 | 1
|  | Ordering |  |  |  | 2022-06-19 | 2022-07-04 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-07-05 | 2022-07-26 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-07-27 | 2022-08-10 | 14
|  | Release of MFC |  |  |  | 2022-08-10 | 2022-08-10 | 1
|  | Manufacturing Lead time |  |  |  | 2022-08-11 | 2022-11-09 | 90
|  | Inspection and Dispatch |  |  |  | 2022-11-10 | 2022-11-25 | 15
|  | Receipt at Site |  |  |  | 2022-11-26 | 2022-12-04 | 9
| Earthing (3000mm long, 40mm dia electrode = 5, and Earthpit Chamber = 5 ) |  | Nos | 61
|  | RFQ to Vendors |  |  |  | 2022-06-18 | 2022-06-18 | 1
|  | Ordering |  |  |  | 2022-06-19 | 2022-07-04 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-07-05 | 2022-07-20 | 15
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-07-21 | 2022-08-04 | 14
|  | Release of MFC |  |  |  | 2022-08-04 | 2022-08-04 | 1
|  | Manufacturing Lead time |  |  |  | 2022-08-05 | 2022-10-19 | 75
|  | Inspection and Dispatch |  |  |  | 2022-10-20 | 2022-11-04 | 15
|  | Receipt at Site |  |  |  | 2022-11-05 | 2022-11-13 | 9
| 33KV Equipment |  |  |  |  | 2022-04-30 | 2023-04-04 | 340
| 33kV Circuit Breaker |  | Set | 1
|  | RFQ to Vendors |  |  |  | 2022-06-13 | 2022-06-13 | 1
|  | Ordering |  |  |  | 2022-06-14 | 2022-06-29 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-06-30 | 2022-07-21 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-07-22 | 2022-08-12 | 21
|  | Release of MFC |  |  |  | 2022-08-12 | 2022-08-12 | 1
|  | Manufacturing Lead time |  |  |  | 2022-08-13 | 2022-10-27 | 75
|  | Inspection and Dispatch |  |  |  | 2022-10-28 | 2022-11-12 | 15
|  | Receipt at Site |  |  |  | 2022-11-13 | 2022-11-21 | 9
| 33kV Lighting Arrestor |  | Nos | 6
|  | RFQ to Vendors |  |  |  | 2022-07-18 | 2022-07-18 | 1
|  | Ordering |  |  |  | 2022-07-19 | 2022-08-03 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-08-04 | 2022-08-25 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-08-26 | 2022-09-16 | 21
|  | Release of MFC |  |  |  | 2022-09-16 | 2022-09-16 | 1
|  | Manufacturing Lead time |  |  |  | 2022-09-17 | 2022-12-01 | 75
|  | Inspection and Dispatch |  |  |  | 2022-12-02 | 2022-12-17 | 15
|  | Receipt at Site |  |  |  | 2022-12-18 | 2022-12-26 | 9
| 33kV Isolator |  | Set | 6
|  | RFQ to Vendors |  |  |  | 2022-05-25 | 2022-05-26 | 1
|  | Ordering |  |  |  | 2022-05-27 | 2022-06-17 | 21
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-06-18 | 2022-07-09 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-07-10 | 2022-07-24 | 14
|  | Release of MFC |  |  |  | 2022-07-24 | 2022-07-24 | 1
|  | Manufacturing Lead time |  |  |  | 2022-07-25 | 2022-10-23 | 90
|  | Inspection and Dispatch |  |  |  | 2022-10-24 | 2022-11-08 | 15
|  | Receipt at Site |  |  |  | 2022-11-09 | 2022-11-17 | 9
| 33kV Current Transformer including 01 JB |  | Nos | 3
|  | RFQ to Vendors |  |  |  | 2022-06-15 | 2022-06-15 | 1
|  | Ordering |  |  |  | 2022-06-16 | 2022-07-01 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-07-02 | 2022-07-23 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-07-24 | 2022-08-14 | 21
|  | Release of MFC |  |  |  | 2022-08-14 | 2022-08-14 | 1
|  | Manufacturing Lead time |  |  |  | 2022-08-15 | 2022-10-29 | 75
|  | Inspection and Dispatch |  |  |  | 2022-10-30 | 2022-11-14 | 15
|  | Receipt at Site |  |  |  | 2022-11-15 | 2022-11-23 | 9
| 33kV Potential Transformer including 01 JB |  | Nos | 1
|  | RFQ to Vendors |  |  |  | 2022-06-15 | 2022-06-15 | 1
|  | Ordering |  |  |  | 2022-06-16 | 2022-07-01 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-07-02 | 2022-07-23 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-07-24 | 2022-08-14 | 21
|  | Release of MFC |  |  |  | 2022-08-14 | 2022-08-14 | 1
|  | Manufacturing Lead time |  |  |  | 2022-08-15 | 2022-10-29 | 75
|  | Inspection and Dispatch |  |  |  | 2022-10-30 | 2022-11-14 | 15
|  | Receipt at Site |  |  |  | 2022-11-15 | 2022-11-23 | 9
| 33kV BPI for Bus |  | Nos | 12
|  | RFQ to Vendors |  |  |  | 2022-07-21 | 2022-07-21 | 1
|  | Ordering |  |  |  | 2022-07-22 | 2022-08-05 | 14
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-08-06 | 2022-08-20 | 14
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-08-21 | 2022-09-04 | 14
|  | Release of MFC |  |  |  | 2022-09-04 | 2022-09-04 | 1
|  | Manufacturing Lead time |  |  |  | 2022-09-05 | 2022-11-04 | 60
|  | Inspection and Dispatch |  |  |  | 2022-11-05 | 2022-11-20 | 15
|  | Receipt at Site |  |  |  | 2022-11-21 | 2022-11-29 | 9
| Bay Marshelling Boxes in 33kV yard |  | Nos | 1
|  | RFQ to Vendors |  |  |  | 2022-08-20 | 2022-08-20 | 1
|  | Ordering |  |  |  | 2022-08-21 | 2022-09-05 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-09-06 | 2022-09-27 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-09-28 | 2022-10-19 | 21
|  | Release of MFC |  |  |  | 2022-10-19 | 2022-10-19 | 1
|  | Manufacturing Lead time |  |  |  | 2022-10-20 | 2022-12-19 | 60
|  | Inspection and Dispatch |  |  |  | 2022-12-20 | 2023-01-04 | 15
|  | Receipt at Site |  |  |  | 2023-01-05 | 2023-01-13 | 9
| CRP for 33kV GIS Building |  | Lot | 1
|  | RFQ to Vendors |  |  |  | 2022-07-01 | 2022-07-01 | 1
|  | Ordering |  |  |  | 2022-07-02 | 2022-07-16 | 14
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-07-17 | 2022-08-07 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-08-08 | 2022-08-29 | 21
|  | Release of MFC |  |  |  | 2022-08-29 | 2022-08-29 | 110
|  | Manufacturing Lead time |  |  |  | 2022-08-30 | 2022-10-29 | 60
|  | Inspection and Dispatch |  |  |  | 2022-10-30 | 2022-11-14 | 15
|  | Receipt at Site |  |  |  | 2022-11-15 | 2022-11-23 | 9
| LT Panel |  | Lot | 1
|  | Placement of Offer |  |  |  | 2022-07-01 | 2022-07-01 | 1
|  | Submission of Drawing |  |  |  | 2022-07-02 | 2022-07-16 | 14
|  | Receipt of Drawing Approval |  |  |  | 2022-07-17 | 2022-08-07 | 21
|  | Manufacturing Claearance |  |  |  | 2022-08-08 | 2022-08-29 | 21
|  | Inspection & issuance of Inspection Certificate |  |  |  | 2022-08-29 | 2022-08-29 | 110
|  | Manufacturing Lead time |  |  |  | 2022-08-30 | 2022-10-29 | 60
|  | Inspection and Dispatch |  |  |  | 2022-10-30 | 2022-11-14 | 15
|  | Receipt at Site |  |  |  | 2022-11-15 | 2022-11-23 | 9
| 33kV Gas Insulated Substation (GIS) Switchgear |  | Nos | 1
|  | RFQ to Vendors |  |  |  | 2022-04-30 | 2022-04-30 | 1
|  | Ordering |  |  |  | 2022-05-01 | 2022-05-22 | 21
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-05-23 | 2022-06-13 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-06-14 | 2022-07-05 | 21
|  | Release of MFC |  |  |  | 2022-07-05 | 2022-07-05 | 1
|  | Manufacturing Lead time |  |  |  | 2022-07-06 | 2023-01-02 | 180
|  | Inspection and Dispatch |  |  |  | 2023-01-03 | 2023-01-24 | 21
|  | Receipt at Site |  |  |  | 2023-01-25 | 2023-02-09 | 15
| 25/30 MVA 33/11.5 kV ONAN/ONAF Transformer |  | Nos | 3
|  | RFQ to Vendors |  |  |  | 2022-05-30 | 2022-05-30 | 1
|  | Ordering |  |  |  | 2022-05-31 | 2022-06-21 | 21
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-06-22 | 2022-07-13 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-07-14 | 2022-08-04 | 21
|  | Release of MFC |  |  |  | 2022-08-04 | 2022-08-04 | 1
|  | Manufacturing Lead time |  |  |  | 2022-08-05 | 2023-03-03 | 210
|  | Inspection and Dispatch |  |  |  | 2023-03-04 | 2023-03-19 | 15
|  | Receipt at Site |  |  |  | 2023-03-20 | 2023-03-28 | 9
| Neutral Grounding Resistor (NGR) |  | Nos | 3
|  | RFQ to Vendors |  |  |  | 2022-08-28 | 2022-08-28 | 1
|  | Ordering |  |  |  | 2022-08-29 | 2022-09-13 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-09-14 | 2022-10-05 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-10-06 | 2022-10-27 | 21
|  | Release of MFC |  |  |  | 2022-10-27 | 2022-10-27 | 1
|  | Manufacturing Lead time |  |  |  | 2022-10-28 | 2023-01-26 | 90
|  | Inspection and Dispatch |  |  |  | 2023-01-27 | 2023-02-11 | 15
|  | Receipt at Site |  |  |  | 2023-02-12 | 2023-02-20 | 9
| GIB (Gas Insulated Bus) |  | Nos | 3
|  | RFQ to Vendors |  |  |  | 2022-08-28 | 2022-08-28 | 1
|  | Ordering |  |  |  | 2022-08-29 | 2022-09-13 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-09-14 | 2022-10-05 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-10-06 | 2022-10-27 | 21
|  | Release of MFC |  |  |  | 2022-10-27 | 2022-10-27 | 1
|  | Manufacturing Lead time |  |  |  | 2022-10-28 | 2023-01-26 | 90
|  | Inspection and Dispatch |  |  |  | 2023-01-27 | 2023-02-11 | 15
|  | Receipt at Site |  |  |  | 2023-02-12 | 2023-02-20 | 9
| HT Cables (3C * 240 sq.mm) |  | Mtr | 11000
|  | RFQ to Vendors |  |  |  | 2022-04-30 | 2022-04-30 | 1
|  | Ordering |  |  |  | 2022-05-01 | 2022-05-16 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-05-17 | 2022-06-07 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-06-08 | 2022-06-29 | 21
|  | Release of MFC |  |  |  | 2022-06-29 | 2022-06-29 | 1
|  | Release of MFC |  |  |  | 2022-06-30 | 2022-11-12 | 135
|  | Release of MFC |  |  |  | 2022-11-13 | 2022-11-28 | 15
|  | Release of MFC |  |  |  | 2022-11-29 | 2022-12-07 | 9
| LT Power / Control Cables and accesssories |  | Mtr | 9200
|  | RFQ to Vendors |  |  |  | 2022-06-30 | 2022-06-30 | 1
|  | Ordering |  |  |  | 2022-07-01 | 2022-07-16 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-07-17 | 2022-08-07 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-08-08 | 2022-08-29 | 21
|  | Release of MFC |  |  |  | 2022-08-29 | 2022-08-29 | 1
|  | Manufacturing Lead time |  |  |  | 2022-08-30 | 2023-01-27 | 150
|  | Inspection and Dispatch |  |  |  | 2023-01-28 | 2023-02-12 | 15
|  | Receipt at Site |  |  |  | 2023-02-13 | 2023-02-21 | 9
| Cable Termination Kits - Straight Through & End Termaintion |  | Lot | 1
|  | RFQ to Vendors |  |  |  | 2022-07-15 | 2022-07-15 | 1
|  | Ordering |  |  |  | 2022-07-16 | 2022-07-31 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-08-01 | 2022-08-22 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-08-23 | 2022-09-13 | 21
|  | Release of MFC |  |  |  | 2022-09-13 | 2022-09-13 | 1
|  | Manufacturing Lead time |  |  |  | 2022-09-14 | 2022-12-13 | 90
|  | Inspection and Dispatch |  |  |  | 2022-12-14 | 2022-12-29 | 15
|  | Receipt at Site |  |  |  | 2022-12-30 | 2023-01-07 | 9
| Cable Trench (outdoor switchyard and GIS.) |  | Mtr | 1845
|  | RFQ to Vendors |  |  |  | 2022-08-01 | 2022-08-01 | 1
|  | Ordering |  |  |  | 2022-08-02 | 2022-08-17 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-08-18 | 2022-09-08 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-09-09 | 2022-09-30 | 21
|  | Release of MFC |  |  |  | 2022-09-30 | 2022-09-30 | 1
|  | Manufacturing Lead time |  |  |  | 2022-10-01 | 2022-12-30 | 90
|  | Inspection and Dispatch |  |  |  | 2022-12-31 | 2023-01-15 | 15
|  | Receipt at Site |  |  |  | 2023-01-16 | 2023-01-24 | 9
| GI Conduit |  | Nos | 100
|  | Placement of Offer |  |  |  | 2022-06-18 | 2022-06-18 | 1
|  | Submission of Drawing |  |  |  | 2022-06-19 | 2022-07-04 | 15
|  | Receipt of Drawing Approval |  |  |  | 2022-07-05 | 2022-07-19 | 14
|  | Manufacturing Claearance |  |  |  | 2022-07-20 | 2022-08-03 | 14
|  | Inspection & issuance of Inspection Certificate |  |  |  | 2022-08-03 | 2022-08-03 | 1
|  | Manufacturing Lead time |  |  |  | 2022-08-04 | 2022-11-02 | 90
|  | Inspection and Dispatch |  |  |  | 2022-11-03 | 2022-11-18 | 15
|  | Receipt at Site |  |  |  | 2022-11-19 | 2022-11-27 | 9
| HDPE Pipe |  | Mtr | 110
|  | Placement of Offer |  |  |  | 2022-06-15 | 2022-06-15 | 1
|  | Submission of Drawing |  |  |  | 2022-06-16 | 2022-07-01 | 15
|  | Receipt of Drawing Approval |  |  |  | 2022-07-02 | 2022-07-17 | 15
|  | Manufacturing Claearance |  |  |  | 2022-07-18 | 2022-08-08 | 21
|  | Inspection & issuance of Inspection Certificate |  |  |  | 2022-08-08 | 2022-08-08 | 1
|  | Manufacturing Lead time |  |  |  | 2022-08-09 | 2022-10-23 | 75
|  | Inspection and Dispatch |  |  |  | 2022-10-24 | 2022-11-08 | 15
|  | Receipt at Site |  |  |  | 2022-11-09 | 2022-11-17 | 9
| Battery / Battery Chargery |  | Set/Nos | 4
|  | RFQ to Vendors |  |  |  | 2022-11-15 | 2022-11-15 | 1
|  | Ordering |  |  |  | 2022-11-16 | 2022-12-01 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-12-02 | 2022-12-17 | 15
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-12-18 | 2023-01-08 | 21
|  | Release of MFC |  |  |  | 2023-01-08 | 2023-01-08 | 1
|  | Manufacturing Lead time |  |  |  | 2023-01-09 | 2023-03-10 | 60
|  | Inspection and Dispatch |  |  |  | 2023-03-11 | 2023-03-26 | 15
|  | Receipt at Site |  |  |  | 2023-03-27 | 2023-04-04 | 9
| ACDB/DCDB |  | Lot | 1
|  | RFQ to Vendors |  |  |  | 2022-11-15 | 2022-11-15 | 1
|  | Ordering |  |  |  | 2022-11-16 | 2022-12-01 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-12-02 | 2022-12-17 | 15
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-12-18 | 2023-01-08 | 21
|  | Release of MFC |  |  |  | 2023-01-08 | 2023-01-08 | 1
|  | Manufacturing Lead time |  |  |  | 2023-01-09 | 2023-03-10 | 60
|  | Inspection and Dispatch |  |  |  | 2023-03-11 | 2023-03-26 | 15
|  | Receipt at Site |  |  |  | 2023-03-27 | 2023-04-04 | 9
| NIFPS System for transformer |  | Lot | 1
|  | RFQ to Vendors |  |  |  | 2022-09-01 | 2022-09-01 | 1
|  | Ordering |  |  |  | 2022-09-02 | 2022-09-17 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-09-18 | 2022-10-03 | 15
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-10-04 | 2022-10-25 | 21
|  | Release of MFC |  |  |  | 2022-10-25 | 2022-10-25 | 1
|  | Manufacturing Lead time |  |  |  | 2022-10-26 | 2022-12-25 | 60
|  | Inspection and Dispatch |  |  |  | 2022-12-26 | 2023-01-10 | 15
|  | Receipt at Site |  |  |  | 2023-01-11 | 2023-01-19 | 9
| Illumination System |  | Lot | 1
|  | RFQ to Vendors |  |  |  | 2022-11-15 | 2022-11-15 | 1
|  | Ordering |  |  |  | 2022-11-16 | 2022-12-01 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-12-02 | 2022-12-17 | 15
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-12-18 | 2023-01-08 | 21
|  | Release of MFC |  |  |  | 2023-01-08 | 2023-01-08 | 1
|  | Manufacturing Lead time |  |  |  | 2023-01-09 | 2023-03-10 | 60
|  | Inspection and Dispatch |  |  |  | 2023-03-11 | 2023-03-26 | 15
|  | Receipt at Site |  |  |  | 2023-03-27 | 2023-04-04 | 9
11kV Switchgear Building
| 11kV Isolator - wall mounted |  | Nos | 3
|  | RFQ to Vendors |  |  |  | 2022-05-25 | 2022-05-26 | 1
|  | Ordering |  |  |  | 2022-05-27 | 2022-06-17 | 21
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-06-18 | 2022-07-09 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-07-10 | 2022-07-24 | 14
|  | Release of MFC |  |  |  | 2022-07-24 | 2022-07-24 | 1
|  | Manufacturing Lead time |  |  |  | 2022-07-25 | 2022-10-23 | 90
|  | Inspection and Dispatch |  |  |  | 2022-10-24 | 2022-11-08 | 15
|  | Receipt at Site |  |  |  | 2022-11-09 | 2022-11-17 | 9
| LT Power / Control Cables and accesssories |  | Mtr | 10200
|  | RFQ to Vendors |  |  |  | 2022-06-30 | 2022-06-30 | 1
|  | Ordering |  |  |  | 2022-07-01 | 2022-07-16 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-07-17 | 2022-08-07 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-08-08 | 2022-08-29 | 21
|  | Release of MFC |  |  |  | 2022-08-29 | 2022-08-29 | 1
|  | Manufacturing Lead time |  |  |  | 2022-08-30 | 2023-01-27 | 150
|  | Inspection and Dispatch |  |  |  | 2023-01-28 | 2023-02-12 | 15
|  | Receipt at Site |  |  |  | 2023-02-13 | 2023-02-21 | 9
| Cable Trench (outdoor switchyard and GIS.) |  | Mtr | 1200
|  | RFQ to Vendors |  |  |  | 2022-08-01 | 2022-08-01 | 1
|  | Ordering |  |  |  | 2022-08-02 | 2022-08-17 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-08-18 | 2022-09-08 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-09-09 | 2022-09-30 | 21
|  | Release of MFC |  |  |  | 2022-09-30 | 2022-09-30 | 1
|  | Manufacturing Lead time |  |  |  | 2022-10-01 | 2022-12-30 | 90
|  | Inspection and Dispatch |  |  |  | 2022-12-31 | 2023-01-15 | 15
|  | Receipt at Site |  |  |  | 2023-01-16 | 2023-01-24 | 9
| Indoor Panel |  | Lot | 1
|  | RFQ to Vendors |  |  |  | 2022-07-01 | 2022-07-01 | 1
|  | Ordering |  |  |  | 2022-07-02 | 2022-07-16 | 14
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-07-17 | 2022-08-07 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-08-08 | 2022-08-29 | 21
|  | Release of MFC |  |  |  | 2022-08-29 | 2022-08-29 | 110
|  | Manufacturing Lead time |  |  |  | 2022-08-30 | 2022-10-29 | 60
|  | Inspection and Dispatch |  |  |  | 2022-10-30 | 2022-11-14 | 15
|  | Receipt at Site |  |  |  | 2022-11-15 | 2022-11-23 | 9
| LT Panel |  | Lot | 1
|  | Placement of Offer |  |  |  | 2022-07-01 | 2022-07-01 | 1
|  | Submission of Drawing |  |  |  | 2022-07-02 | 2022-07-17 | 15
|  | Receipt of Drawing Approval |  |  |  | 2022-07-18 | 2022-08-08 | 21
|  | Manufacturing Claearance |  |  |  | 2022-08-09 | 2022-08-30 | 21
|  | Inspection & issuance of Inspection Certificate |  |  |  | 2022-08-30 | 2022-08-30 | 1
|  | Manufacturing Lead time |  |  |  | 2022-08-31 | 2022-11-29 | 90
|  | Inspection and Dispatch |  |  |  | 2022-11-30 | 2022-12-15 | 15
|  | Receipt at Site |  |  |  | 2022-12-16 | 2022-12-24 | 9
| CRP |  | Lot | 1
|  | RFQ to Vendors |  |  |  | 2022-07-01 | 2022-07-01 | 1
|  | Ordering |  |  |  | 2022-07-02 | 2022-07-17 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-07-18 | 2022-08-08 | 21
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-08-09 | 2022-08-30 | 21
|  | Release of MFC |  |  |  | 2022-08-30 | 2022-08-30 | 1
|  | Manufacturing Lead time |  |  |  | 2022-08-31 | 2022-11-29 | 90
|  | Inspection and Dispatch |  |  |  | 2022-11-30 | 2022-12-15 | 15
|  | Receipt at Site |  |  |  | 2022-12-16 | 2022-12-24 | 9
| GI Conduit |  | Nos | 140
|  | Placement of Offer |  |  |  | 2022-06-18 | 2022-06-18 | 1
|  | Submission of Drawing |  |  |  | 2022-06-19 | 2022-07-04 | 15
|  | Receipt of Drawing Approval |  |  |  | 2022-07-05 | 2022-07-19 | 14
|  | Manufacturing Claearance |  |  |  | 2022-07-20 | 2022-08-03 | 14
|  | Inspection & issuance of Inspection Certificate |  |  |  | 2022-08-03 | 2022-08-03 | 1
|  | Manufacturing Lead time |  |  |  | 2022-08-04 | 2022-11-02 | 90
|  | Inspection and Dispatch |  |  |  | 2022-11-03 | 2022-11-18 | 15
|  | Receipt at Site |  |  |  | 2022-11-19 | 2022-11-27 | 9
| Battery / Battery Chargery |  | Set/Nos | 4
|  | RFQ to Vendors |  |  |  | 2022-11-15 | 2022-11-15 | 1
|  | Ordering |  |  |  | 2022-11-16 | 2022-12-01 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-12-02 | 2022-12-17 | 15
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-12-18 | 2023-01-08 | 21
|  | Release of MFC |  |  |  | 2023-01-08 | 2023-01-08 | 1
|  | Manufacturing Lead time |  |  |  | 2023-01-09 | 2023-03-10 | 60
|  | Inspection and Dispatch |  |  |  | 2023-03-11 | 2023-03-26 | 15
|  | Receipt at Site |  |  |  | 2023-03-27 | 2023-04-04 | 9
| Illumination System |  | Lot | 1
|  | RFQ to Vendors |  |  |  | 2022-11-15 | 2022-11-15 | 1
|  | Ordering |  |  |  | 2022-11-16 | 2022-12-01 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-12-02 | 2022-12-17 | 15
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-12-18 | 2023-01-08 | 21
|  | Release of MFC |  |  |  | 2023-01-08 | 2023-01-08 | 1
|  | Manufacturing Lead time |  |  |  | 2023-01-09 | 2023-03-10 | 60
|  | Inspection and Dispatch |  |  |  | 2023-03-11 | 2023-03-26 | 15
|  | Receipt at Site |  |  |  | 2023-03-27 | 2023-04-04 | 9
Other Utilities
| AC |  | Nos | 8
|  | RFQ to Vendors |  |  |  | 2022-10-20 | 2022-10-20 | 1
|  | Ordering |  |  |  | 2022-10-21 | 2022-11-05 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-11-06 | 2022-11-21 | 15
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-11-22 | 2022-12-13 | 21
|  | Release of MFC |  |  |  | 2022-12-13 | 2022-12-13 | 1
|  | Manufacturing Lead time |  |  |  | 2022-12-14 | 2023-03-14 | 90
|  | Inspection and Dispatch |  |  |  | 2023-03-15 | 2023-03-30 | 15
|  | Receipt at Site |  |  |  | 2023-03-31 | 2023-04-08 | 9
| Ventilation system (Both GIS and Oxygen Plant) |  | Lot | 1
|  | RFQ to Vendors |  |  |  | 2022-10-20 | 2022-10-20 | 1
|  | Ordering |  |  |  | 2022-10-21 | 2022-11-05 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-11-06 | 2022-11-21 | 15
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-11-22 | 2022-12-13 | 21
|  | Release of MFC |  |  |  | 2022-12-13 | 2022-12-13 | 1
|  | Manufacturing Lead time |  |  |  | 2022-12-14 | 2023-03-14 | 90
|  | Inspection and Dispatch |  |  |  | 2023-03-15 | 2023-03-30 | 15
|  | Receipt at Site |  |  |  | 2023-03-31 | 2023-04-08 | 9
| Fire Protection system for 33kV GIS |  | Nos | 1
|  | RFQ to Vendors |  |  |  | 2022-10-20 | 2022-10-20 | 1
|  | Ordering |  |  |  | 2022-10-21 | 2022-11-05 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-11-06 | 2022-11-21 | 15
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-11-22 | 2022-12-13 | 21
|  | Release of MFC |  |  |  | 2022-12-13 | 2022-12-13 | 1
|  | Manufacturing Lead time |  |  |  | 2022-12-14 | 2023-03-14 | 90
|  | Inspection and Dispatch |  |  |  | 2023-03-15 | 2023-03-30 | 15
|  | Receipt at Site |  |  |  | 2023-03-31 | 2023-04-08 | 9
| Fire Fighting for 220kV Bay |  | Lot | 1
|  | RFQ to Vendors |  |  |  | 2022-10-20 | 2022-10-20 | 1
|  | Ordering |  |  |  | 2022-10-21 | 2022-11-05 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-11-06 | 2022-11-21 | 15
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-11-22 | 2022-12-13 | 21
|  | Release of MFC |  |  |  | 2022-12-13 | 2022-12-13 | 1
|  | Manufacturing Lead time |  |  |  | 2022-12-14 | 2023-03-14 | 90
|  | Inspection and Dispatch |  |  |  | 2023-03-15 | 2023-03-30 | 15
|  | Receipt at Site |  |  |  | 2023-03-31 | 2023-04-08 | 9
| Telecommunication System |  | Lot | 1
|  | RFQ to Vendors |  |  |  | 2022-10-20 | 2022-10-20 | 1
|  | Ordering |  |  |  | 2022-10-21 | 2022-11-05 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-11-06 | 2022-11-21 | 15
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-11-22 | 2022-12-13 | 21
|  | Release of MFC |  |  |  | 2022-12-13 | 2022-12-13 | 1
|  | Manufacturing Lead time |  |  |  | 2022-12-14 | 2023-03-14 | 90
|  | Inspection and Dispatch |  |  |  | 2023-03-15 | 2023-03-30 | 15
|  | Receipt at Site |  |  |  | 2023-03-31 | 2023-04-08 | 9
| Sundary Items - Cable Tray / IPS Tube / ACSR Conductor |  | Lot | 1
|  | RFQ to Vendors |  |  |  | 2022-08-10 | 2022-08-10 | 1
|  | Ordering |  |  |  | 2022-08-11 | 2022-08-26 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-08-27 | 2022-09-11 | 15
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-09-12 | 2022-10-03 | 21
|  | Release of MFC |  |  |  | 2022-10-03 | 2022-10-03 | 1
|  | Manufacturing Lead time |  |  |  | 2022-10-04 | 2023-01-02 | 90
|  | Inspection and Dispatch |  |  |  | 2023-01-03 | 2023-01-18 | 15
|  | Receipt at Site |  |  |  | 2023-01-19 | 2023-01-27 | 9
MISC and Spare Material
| Safety Eqp, Special tools and tackles |  | Lot | 1
|  | RFQ to Vendors |  |  |  | 2022-10-20 | 2022-10-20 | 1
|  | Ordering |  |  |  | 2022-10-21 | 2022-11-05 | 15
|  | Receipt of Drawing and Documents from Vendor |  |  |  | 2022-11-06 | 2022-11-21 | 15
|  | Approval of Drawings and Documents from Client |  |  |  | 2022-11-22 | 2022-12-13 | 21
|  | Release of MFC |  |  |  | 2022-12-13 | 2022-12-13 | 1
|  | Manufacturing Lead time |  |  |  | 2022-12-14 | 2023-03-14 | 90
|  | Inspection and Dispatch |  |  |  | 2023-03-15 | 2023-03-30 | 15
|  | Receipt at Site |  |  |  | 2023-03-31 | 2023-04-08 | 9
Sample phase title block | CIVIL AND STRUCTURAL WORK |  |  |  |  | 2022-05-15 | 2023-07-03 | 415
33kV GIS BUILDING
|  | EARTH WORK AND EXCAVATION |  |  |  | 2022-05-15 | 2022-05-30 | 15
|  | BUILDING FOUNDATION |  |  |  | 2022-05-30 | 2022-06-19 | 20
|  | SUPER STRUCTURE WORK |  |  |  | 2022-06-20 | 2022-08-10 | 51
|  | BRICK WORK, PLASTERING, FLOORING & FINISHING |  |  |  | 2022-08-10 | 2022-10-29 | 80
|  | PLINTH PROTECTION, ARCHITECHTURAL ETC. |  |  |  | 2022-10-29 | 2022-11-18 | 20
|  | COMPETION OF SUBSTATION BUILDING |  |  |  | 2022-11-18 | 2023-01-08 | 51
11kV Switchgear Buildung
|  | EARTH WORK AND EXCAVATION |  |  |  | 2022-06-15 | 2022-07-05 | 20
|  | BUILDING FOUNDATION |  |  |  | 2022-07-05 | 2022-08-04 | 30
|  | SUPER STRUCTURE WORK |  |  |  | 2022-08-05 | 2022-09-25 | 51
|  | BRICK WORK, PLASTERING, FLOORING & FINISHING |  |  |  | 2022-09-25 | 2022-11-24 | 60
|  | PLINTH PROTECTION, ARCHITECHTURAL ETC. |  |  |  | 2022-11-24 | 2022-12-25 | 31
|  | COMPETION OF SWITCHGEAR BUILDING |  |  |  | 2022-12-25 | 2023-02-24 | 61
YARD FOUNDATIONS
|  | 80 mVA Transformer Foundation |  |  |  | 2022-06-30 | 2022-08-24 | 55
|  | 220 kV Isolator Foundation |  |  |  | 2022-07-01 | 2022-07-22 | 21
|  | 220 kV Circuit Breaker with ladder foundation |  |  |  | 2022-07-01 | 2022-07-17 | 16
|  | 220 kV Current Transformer Foundation |  |  |  | 2022-07-04 | 2022-07-20 | 16
|  | 220 kV Surge/ Lighting Arrestor |  |  |  | 2022-07-04 | 2022-07-20 | 16
|  | 220 kV Bus Post Insulator Foundation |  |  |  | 2022-07-10 | 2022-08-10 | 31
|  | Soak Pit/ Burnt Oil Pit - Including with approved PVC/ RCC Pipe from Transformer Foundation |  |  |  | 2022-07-10 | 2022-08-10 | 31
|  | 33 kV Isolator Foundation |  |  |  | 2022-07-10 | 2022-07-26 | 16
|  | 33 kV Surge/ Lighting Arrestor |  |  |  | 2022-07-10 | 2022-07-21 | 11
|  | 33 kV Circuit Breaker |  |  |  | 2022-07-15 | 2022-07-26 | 11
|  | 33 kV Current Transformer |  |  |  | 2022-07-15 | 2022-07-31 | 16
|  | 33 kV Bus Post Insulatior |  |  |  | 2022-07-19 | 2022-07-30 | 11
|  | Cable Support Structure |  |  |  | 2022-07-05 | 2022-08-29 | 55
Cable Trenches
|  | Section 3-3 (1050 mm Wide) |  |  |  | 2022-07-15 | 2022-08-19 | 35
|  | Section 4-4 (600 mm Wide) |  |  |  | 2022-07-15 | 2022-08-25 | 41
|  | HDD |  |  |  | 2022-12-01 | 2022-12-31 | 30
|  | Low Height Cable Gallery |  |  |  | 2022-11-01 | 2022-12-11 | 40
OTHERS
|  | Concrete Road |  |  |  | 2023-06-06 | 2023-06-21 | 15
|  | Drains |  |  |  | 2023-06-13 | 2023-07-03 | 20
MULSIFIER SYSTEM
|  | FFPH Building |  |  |  | 2022-06-30 | 2022-07-11 | 12
|  | Fire Hydrant Line for 80 MVA Xformer(Only Civil) |  |  |  | 2022-07-10 | 2022-07-26 | 17
| ELECTRICAL INSTALLATION / ERECTION WORK |  |  |  |  | 2022-11-10 | 2023-05-30 | 202
| 220KV Structure Erection |  |  |  |  | 2022-11-10 | 2022-12-10 | 31
| 33KV Structure Erection |  |  |  |  | 2022-11-10 | 2022-12-10 | 31
| 220kV Equipment Erection |  |  |  |  | 2022-12-10 | 2023-01-09 | 31
| 33kV Equipment Erection |  |  |  |  | 2022-12-10 | 2023-01-09 | 31
| 80Mva transformer Erection |  |  |  |  | 2023-01-17 | 2023-02-21 | 36
| Equipement Interconnections |  |  |  |  | 2023-01-09 | 2023-01-29 | 21
| 30Mva Transformer Erection |  |  |  |  | 2023-04-27 | 2023-05-27 | 31
| 11kV Switchgear Erection |  |  |  |  | 2023-05-20 | 2023-05-30 | 11
| HT Cable Laying |  |  |  |  | 2022-11-20 | 2023-02-28 | 101
| GIS (33KV) ERECTION WORK |  |  |  |  | 2023-03-01 | 2023-05-30 | 91
| Control & Relay Panel Erection |  |  |  |  | 2023-01-20 | 2023-01-30 | 11
| LT & Control Cable Laying and Termination |  |  |  |  | 2023-01-25 | 2023-02-14 | 21
| TESTING AND COMMISSIONING |  |  |  |  | 2023-03-01 | 2023-08-15 | 168
| Testing of 80MvA Transformer |  |  |  |  | 2023-03-01 | 2023-03-21 | 20
| Testing of 30MvA Transformer |  |  |  |  | 2023-03-23 | 2023-04-07 | 15
| Testing of 33kV GIS |  |  |  |  | 2023-06-03 | 2023-07-04 | 31
| Testing of Outdoor Equipments ( 220kV & 33kV Bays) |  |  |  |  | 2023-06-03 | 2023-06-19 | 16
| Cable Testing |  |  |  |  | 2023-03-04 | 2023-03-25 | 21
| Relay Testing and coordination with SCADA & Existing CRP |  |  |  |  | 2023-06-29 | 2023-07-15 | 16
| Project Completion |  |  |  |  | 2023-07-15 | 2023-08-15 | 31
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule.
Note on B364: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: INCLUDING CSS
Note on B373: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: INCLUDING CSS
Note on B455: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: INCLUDING CSS
Note on B473: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: INCLUDING CSS